## Slide 1: Responsibility charting (RACI)

## Slide 2: What Is RACI ?
Responsibility Charting
Is a technique for identifying functional areas, key activities, and decision points where ambiguities exist; differences can be brought into the open and resolved through team effort.
The approach enables management to actively participate in the process of systematically describing activities, decisions that have to be accomplished, and to clarify the responsibility that each plays in relation to those activities and decisions.

## Slide 3: Objectives/Benefits
Assist natural work teams in charting roles and responsibilities in a consistent manner
Assist natural work teams with development of implementation tool kits
Clarify individual/departmental roles and responsibilities
Identify accountabilities
Eliminate misunderstandings, encourage teamwork
Reduce duplication of effort
Establish “consults” and “informs” resulting in better communication

## Slide 4: Critical Issue Summary
Roles and Responsibilities | To better understand To improve communications
Accountability | To clarify
Responsibilities | To identify authority
Job responsibility | To empower employees with authority to do it
Role of middle manager | To bring up to speed with organization structure
Approval | To reduce uncertainty of multiple reporting
Opportunity

## Slide 5: Guidelines
Remember new culture philosophy when defining roles and responsibilities
  Eliminate “checkers checking checkers”
  Encourage teamwork
  100% accuracy not always required
Place accountability (A) and responsibility (R) at the level closest to the action or knowledge
There can be only one accountability per activity
Authority must accompany accountability
Minimize the number of consultants (C) and informs (I)
All roles and responsibilities must be documented and communicated

## Slide 6: RACI Stands for:
“A” | Accountable | “The buck stops here”
“R” | Responsible | “The doer”
“C” | Consult | “In the loop”
“I” | Inform | “Keep in the picture”

## Slide 7: Codes
Accountable | Position with yes/no authority
Responsible | Position working on the activity
Consult | Position involved prior to decision or action
Inform | Position that needs to know of the decision or action

## Slide 8: RACI Defined
The individual who is ultimately responsible. Includes yes or no authority and veto power. Only one “A” can be assigned to a function.
The individual(s) who actually completes the task, the doer. This person is responsible for action/implementation. Responsibility can be shared. The degree of responsibility is determined by the individual with the “A”.
The individual(s) to be consulted prior to a final decision or action. This incorporates two-way communication.
The individual(s) who needs to be informed after a decision or action is taken. This incorporates one-way communication.
Accountability
“A”
Responsibility
“R”
Consult “C”
Inform “I”

## Slide 9: Process Steps
Responsibility charting is completed in a six step process:
Introductory meetings are conducted to inform key management of the purpose and requirements of the process
Decision and function lists are developed, analyzed and collated into a master function list.
Responsibility workshops are conducted to agree upon function definitions and to assign codes that describe the type of participation each role will have toward each function. The output is a responsibility chart.
The responsibility charts are documented and reproduced to distribute to all participants and interfacing organizations.
The communication and reinforcement of the new role definitions are accomplished through meetings with all individuals and departments involved.
Follow-up is conducted to ensure that relationships defined in the process are being adhered to and to encourage participants to live the roles.

## Slide 10: The Output Matrix
Roles of Participants
Decisions or Activities
Type or degree of participation

## Slide 11: RACI Charting
Roles and Responsibilities Analysis
Functional Roles
 |  |  | R |  | A |  | C |  | I | C | 
 |  |  | A | R |  | R | C | C | I |  | I
 | Decisions / Functions / Activities |  | C |  | R |  | C | C |  | R | A
 |  |  | C |  | A |  |  | R |  | R | 
 |  |  | I | C |  | R | A |  | C |  | R
 |  |  |  | I |  | C | R | A |  |  | C
Business Processes

## Slide 12: Activity Or Decision List Guidelines
Avoid obvious or generic activities, for example, “attend meetings”
Each activity or decision should begin with a good action verb. Examples:
evaluate | schedule | write | record | determine
operate | monitor | prepare | update | collect
approve | conduct | develop | inspect | train
publish | report | review | authorize | decide
When the action verb implies a judgement or a decision (for example, evaluate, monitor, inspect review), add a phrase to indicate the primary outcome. Examples:
“Monitor phone service handling of customer requests to identify training needs”
“Analyze data to locate source of delay”
Activities or decisions should be short, concise and apply to a role or need, not to a specific person.

## Slide 13: Definitions
 | An action that is one of several sequential steps in the completion of a business process |  | R |  | A |  | C |  | I | C | 
 |  |  | A | R |  | R | C | C | I |  | I
 |  |  | C |  | R |  | C | C |  | R | A
 |  |  | C |  | A |  |  | R |  | R | 
 |  |  | I | C |  | R | A |  | C |  | R
 |  |  |  | I |  | C | R | A |  |  | C
Functional Roles
Decisions / Functions / Activities
A position assigned or assumed to accomplish an activity or sub-activity

## Slide 14: RACI Chart Example
Functional Roles
Decisions / Functions
Employee
Secretary
Supervisor
Region Accounting
1. Document expenses | AR |  |  | 
2. Complete expense form | AR |  |  | C
3. Forward to supervisor | A | R |  | 
4. Review | C |  | AR | 
5. Approve | I |  | AR | 
6. Forward to Region |  | R | A | 

## Slide 15: Chart Analysis And Review
Vertical Analysis
Functional Roles
 | R |  | A |  | C |  | I | C | 
 | A |  |  | R | C | C | I |  | I
 | C |  | R |  | C | C |  | R | A
 | C |  | A |  |  | R |  | R | 
 | I |  |  | R | A |  | C |  | R
 |  |  |  | C | R | A |  |  | C

## Slide 16: Vertical Analysis
Lots of R’s
No empty spaces
No R’s or A’s
Too many A’s
Qualifications
If You Find: Then Ask:
Can or need the individual(s) stay on top of so much? Can the decision/activity be broken into smaller, more manageable functions?
Does the individual(s) need to be involved in so many activities? Are they a “gatekeeper” or could management by exception principles be used?
Can C’s be reduced I’s, or left to the individual’s discretion when something needs particular attention?
Should this functional role be eliminated? Have processes changed to a point where resources should be re-utilized?
Does a proper “segregation of duties” exist? Should other groups be accountable for some of these activities to ensure checks and balances and accurate decision making throughout the process? Is this a “bottleneck” in the process—is everyone waiting for decisions or direction?
Does the type or degree of participation fit the qualifications of this role?

## Slide 17: Chart Analysis And Review
Horizontal analysis
 | R |  | A |  | C |  | I | C | 
 | A |  |  | R | C | C | I |  | I
 | C | C | R |  | C | C |  | R | A
 | I | A |  | R |  |  | C |  | R
 |  |  |  | C | R | A |  |  | C

## Slide 18: Horizontal Analysis
If You Find:
No R’s
Too many R’s
No A’s
Too many A’s
Is job getting done? Some roles may be waiting to approve, be consulted, or informed. No one sees their role to take the initiative.
Is this a sign of “over the wall” activities? “Just get it off my desk ASAP!”
Why not? There must be an “A.” Accountability should be pushed down to the most appropriate level.
Is there confusion? “I though you had it!” It also creates confusion because every person with an “A” has a different view of how it is or should be done.
Then Ask:

## Slide 19: Horizontal Analysis (Cont.)
Too few A’s and R’s
Lots of C’s
Lots of I’s
Every box filled in
If You Find:
The process must slow down while the activity is performed on an “ad hoc” basis. Or the procedure may be outdated and can be streamlined if not needed.
Do all the functional roles really need to be consulted? Are there justifiable benefits in consulting all the roles?
Do all the roles need to be routinely informed or only in exceptional circumstances?
They shouldn’t be. If they are, too many people are involved—usually too many “C’s” and “I’s.”
Then Ask:

## Slide 20: Get Feedback And Buy-in
The RACI chart is shown to representative groups of people covering the roles on the chart
Their builds are captured and the chart is revised as appropriate
The RACI may be validated in conjunction with the other products of the Project Team

## Slide 21: Benefits
Increased productivity through well defined accountability
Reduced scrap and rework because need specifications are clarified
Increased capacity by eliminating overlaps and redundancies
Streamlined organization structure by collapsing unneeded layers and placing accountability where it belongs
Better trained people by involving them in workshops where fellow workers discuss all roles and functions
Better planning process because of more participation of team members as a result of building communication interfaces (consult and inform)

## Slide 22: The RACI Process Provides a Clear Basis for Defining Changes to Accountabilities and Structure
Project Management—to assign responsibilities and ensure tasks get done
“As Is” Analysis—to diagnose problems in the organisation
“To Be” Design—to create a new organisation structure that meets the needs of the “To Be” design
Definition
Use
Who is RESPONSIBLE?
Who is RESPONSIBLE?
R A C I
The person who has to do it (the doer)
Who is ACCOUNTABLE?
Who is ACCOUNTABLE?
The person who makes the final decision and has ultimate ownership
Who is CONSULTED?
Who is CONSULTED?
The person who must be consulted before a decision or action is taken
Who is INFORMED?
Who is INFORMED?
The person who must be informed that a decision or action has been taken
Process
Facilitator
Line
Facilitator
Setter
Operator
Plan activities
I
A
A
I
Prepare detail
C
A/R
I
Change process docume
ennttss A
R
I
Perform change
I
A
R
R
Activities | Process Facilitator | Line Facilitator | Setter | Operator
Plan activities | I A I | A A I C A/R I R I A R R |  | 
Prepare detail |  |  |  | 
Change process docum |  |  |  | 
Perform change |  |  |  | 
Sample RACI Matrix:
PROCESS: Making a process
Functional Roles
change
RACI Analysis:
If you find:
Horizontal
Horizontal
Lots of Rs No Rs or As
More than one A
Lots of Cs Lots of Is
Too many people involved?
Why do it? Is the job getting done? Confusion, indecision?
Does everyone consulted add value? Do they all need to know?
If you find:
Vertical
Vertical
Lots of Rs
No empty space
No Rs or As Too many As
Too much work?
Too much work? Too much consultation?
Can the function be eliminated?
Is accountability at the right level? Is the organisation too hierarchical?